## Blad1
Activiteit: | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Plan van Aanpak | bar: Week 1 to Week 2
Ontwerpen: | bar: Week 2 to Week 3
ERD's | bar: Week 2
PSD's | bar: Week 2
Wireframes | bar: Week 3
Webdashboard: | bar: Week 4 to Week 10
Maken | bar: Week 4 to Week 10
Connectie DB | bar: Week 4
Connectie DaHaus | bar: Week 5
Onderzoeksverslag